## overview
[10 empty] | 23 | [11 empty] | 2024 |  |  |  |  | 2025 |  |  |  | 2026 | 2027 | 2028
Development Phase Programme | ptsmay 27th | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr - June | July - Sept | Oct - Dec | Jan - Mar 2025 | Apr - Jun 25 | Jul - Sept 25 | Oct - Dec 25 | Jan - Mar 26 | July
Finalise Technical Project Manager Brief
Advertise Technical Project Manager Brief 4wks | bar: Jun to Jul
Interview Technical Project Manager 1wk | bar: Aug
References and Sign Off 2wks | bar: Aug
Appointment 1wk | bar: Aug
Target Start Date | bar: Aug to Sep
Collate reports for Mid Term Review | bar: 23 Jul to 23 Aug
Convene Fundraising Working group and create action plan | bar: Jun
Finalise Fundraising Consultant Brief | bar: Jun
Advertise Fundraising Consultant Brief | bar: Jun
Interviews Fundraising Consultant | bar: Jul
References and Sign Off | bar: Jul
Appointment | bar: Jul
Target start date | bar: Aug
Fundraiser Event(s) | bar: Sep
Deliver update on fundraising for Mid Term Review | bar: 23 Aug
Meet Fundraising target | bar: 23 Oct
Finalise Design Team Brief
Advertise Design Team Brief | bar: Oct
Interviews Design Team | bar: Nov
References and Sign Off | bar: Nov
Appointment | bar: Nov
Target Start Date | bar: Dec
Site surveys and investigations | bar: 23 Jun to 23 Jul
Consultation with statutory consultees | bar: 23 May to 23 Jul
Deliver Capital works design RIBA 2+ at Mid term review | bar: 23 Aug
Prepare planning application | bar: 23 Sep
Deliver Capital works design phase RIBA 3 for Delivery Phase bid | bar: 23 Nov
Finalise Business Plan Consultant Brief
Advertise Business Plan Consultant Brief | bar: Oct
Interviews Business Plan Consultant | bar: Nov
References and Sign Off | bar: Nov
Appointment | bar: Nov
Target Start Date | bar: Dec
Delivers draft Business Plan for Mid Term Review | bar: 23 Aug
Delivers final Business Plan | bar: 23 Nov
Finalise Evaluation Consultant Brief
Advertise Evaluation Consultant Brief | bar: Oct
Interviews Evaluation Consultant | bar: Nov
References and Sign Off | bar: Nov
Appointment | bar: Nov
Target Start Date | bar: Dec
Consultation - internal and external (key activity) | bar: Jan to 23 Jul
Delivers draft Evaluation Framework for Mid Term Review | bar: 23 Aug
Delivers Evaluation Framework for Project | bar: 23 Nov
Delivers Evaluation of the Development Phase | bar: 23 Oct to 23 Nov
Finalise Activity Plan Consultant Brief
Advertise Activity Plan Consultant Brief
Interview Activity Plan Consultant | bar: Oct
References and Sign Off | bar: Nov
Appointment | bar: Nov
Target Start Date | bar: Nov
Consultation - internal and external (key activity) | bar: Dec to 23 Jul
Delivers draft Activity Plan for Mid Term Review | bar: 23 Aug
Delivers final Activity Plan | bar: 23 Nov
Finalise Interpretation Plan Development and Fit Out Design Consultant Brief
Advertise Interpretation Plan Development and Fit Out Consultant Brief | bar: Jul; Oct
Interview Interpretation Plan Development and Fit Out Consultant | bar: Aug; Nov
References and Sign Off | bar: Aug; Nov
Appointment | bar: Aug; Nov
Target Start Date | bar: Dec
Consultation - internal and external (key activity) | bar: Jan to 23 Jul
Delivers draft Interpretation Plan RIBA 2 | bar: 23 Mar
Delivers draft Interpretation Plan RIBA 2+for Mid Term review | bar: 23 Aug
Delivers final RIBA3 Interpretation Plan | bar: 23 Nov
Finalise Administration Back fill post
Advertise Administration Back fill post
Interview Administration Back fill post
References and Sign Off
Appointment | bar: Jun
Target start date | bar: Jun
End of contract | bar: 23 Jun
Seek advice on VAT - financial advice, legal advice, make any legal change, plan financial processes change, review and plan price change (if necessary) | bar: Jun
Action Plan for VAT Registration in Delivery Phase | bar: Jul to 23 May
Confirm date for VAT Registration with NLHF | bar: 23 Nov
Register for VAT - earliest
Revise lease at Courthouse Museum | bar: Jun to Oct
Sign, seal and deliver new Courthouse Lease | bar: Nov
Agree TOR and membership of Project Board (PB)
Project Board meetings | bar: Jun to Jul; Nov; 23 Mar; 23 Jul; 23 Oct
Review Risk Register | bar: Jun to Jul; Nov; 23 Mar; 23 Jul; 23 Oct
NPO notification | bar: Nov
Permission to start April 2022
Claims 50%, 40%, 10% | bar: Jul; 23 Sep; 23 Jan
MID TERM REVIEW
Prepare papers (2 weeks before Mid Term Review Meeting date) | bar: 23 Jul
Mid Term Review meeting held | bar: 23 Aug
Act on feedback from Mid Term Review (2 weeks after meeting) | bar: 23 Sep
Target permission to start date for Delivery Phase | bar: 2024 Mar
Reappointment of professional team
Appointment of contractor and mobilisation
Construction period
Fit out
Length of Activity Plan (3 years)
Completion and summative evaluation

## PM
Development Phase Programme | PTS 27 May | Advertise Jun 27th | deadline for apps 23rd July | shortlist w/c 24th July | Interview 9,10,11 August | sign off 12th - 25th August | appt w/c 28th August | start 5th Sept | Sept | Oct | Nov | Dec | 2023-01-01 | Feb | Mar | Apr | May | June | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr - June | July - Sept | Oct - Dec | Jan - Mar 2025 | Apr - Jun 25 | Jul - Sept 25 | Oct - Dec 25 | Jan - Mar 26 | July
Finalise Technical Project Manager Brief
Advertise Technical Project Manager Brief 4wks
Interview Technical Project Manager 1wk
References and Sign Off 2wks
Appointment 1wk
Target Start Date
Collate reports for Mid Term Review